## All Sprints
Requirement ID | Description of Requirements | Story Points | Priority | Sprint No. | Team Member Assigned
1.1 | Create GitHub Repository | 1 | 1 | 1 | Janna
1.2 | Configure TypeScript/React | 2 | 1 | 1 | Addison
2.1 | Utilize FullCalendar.io | 3 | 1 | 1 | Addison
2.2 | Clean Daily Calendar View | 1 | 1 | 4 | Addison
2.3 | Clean Weekly Calendar View | 1 | 1 | 4 | Addison
2.4 | Clean Monthly Calendar View | 1 | 1 | 4 | Addison
3.1 | "Schedule New Task" button | 2 | 1 | 1 | Janna
3.2 | Create New Task Label Button | 2 | 1 | 1 | Janna
3.3 | Display created task labels as buttons | 2 | 1 | 1 | Janna
3.4 | User-estimated task time input form | 2 | 1 | 1 | Janna
3.5 | User-inputted drive-time input form | 2 | 1 | 1 | Janna
3.6 | Task Deadline (Time/Date) Input form | 2 | 1 | 1 | Elizabeth
3.7 | Priority level buttons | 2 | 1 | 1 | Elizabeth
3.8 | Task description box | 1 | 1 | 1 | Janna
3.9 | Add Task Button | 1 | 1 | 1 | Janna
4.1 | Schedule Task Button | 1 | 1 | 2 | Janna
4.2 | Scheduling Time Ranges | 2 | 1 | 2 | Janna
4.3 | Scheduling Date Ranges | 2 | 1 | 2 | Janna
4.4 | Fetch tasks from database to list on page | 3 | 1 | 2 | Janna
5.1 | Schedule task based on priority and/or past data | 8 | 1 | 2 | Hunter
5.2 | Add newly scheduled task to calendar interface | 3 | 1 | 2 | Anya
6.1 | Setup database | 5 | 1 | 2 | Addison
6.2 | Create and setup database tables | 3 | 1 | 2 | Addison
6.3 | Add sample data to database | 3 | 1 | 2 | Addison
6.4 | Enforce Encryption on All Communications | 2 | 2 | 3 | Addison
7.1 | Link Google Account Button | 1 | 2 | 2 | Marco
7.2 | Backend logic Sign-in with Google API | 3 | 2 | 2 | Marco
7.3 | Link Google Account to database | 2 | 2 | 1 | Anya
7.4 | Account Signout button | 1 | 2 | 2 | Marco
7.5 | Create mock Event results | 1 | 2 | 2 | Marco
7.6 | Pull Google Calendar events to in-app calendar | 3 | 2 | 2 | Elizabeth
7.7 | Push in-app scheduled events to Google calendar | 3 | 2 | 4 | Elizabeth
7.8 | Create UI picklist for selecting a calendar to import | 5 | 2 | 4 | Marco
9.1 | Display task timer page | 2 | 3 | 3 | Anya
9.2 | Display list of tasks | 2 | 3 | 1 | Janna
9.3 | Display timer with start/stop button | 2 | 3 | 1 | Janna
9.4 | Save task time from timer to database | 2 | 3 | 3 | Addison
9.5 | Remove task from list (without completion) | 1 | 3 | 3 | Janna
9.6 | Mark task complete | 1 | 3 | 3 | Janna
9.7 | Task completion time form | 2 | 3 | 3 | Janna
10 | Optimize web application for mobile/desktop | 5 | 3 | 3 | Addison
11.1 | Customizable mascot design | 5 | 3 | 3 | Elizabeth
11.2 | Add mascot customization page | 3 | 3 | 4 | Janna
11.3 | Display mascot options | 3 | 3 | 4 | Janna
11.4 | Save mascot selection in database | 2 | 3 | 4 | Janna
11.5 | Add mascot selection to other pages | 2 | 3 | 5 | Janna
12.1 | Improve add task and task list user interface | 3 | 3 | 4 | Janna
13.1 | Task completion statistics | 5 | 4 | 2026-04-05 | Addison
13.2 | Statistics leaderboard | 5 | 4 |  | Marco
13.3 | Task speedrun mode | 5 | 4 | 4 | Elizabeth
14.1 | Update Home page UI/UX to a dashboard | 3 | 4 | 5 | Janna
14.2 | Display basic task information on dashboard | 3 | 4 | 5 | Janna
15 | Update UI/UX | 4 | 4 | 5 | Addison
15.1 | Make categories per user and show avgs | 3 | 4 | 5 | Elizabeth

## Sprint 1
Requirement ID | Description of Requirements | Story Points | Priority | Sprint No. | Team Member Assigned
1.1 | Create GitHub Repository | 1 | 1 | 1 | Janna
1.2 | Configure TypeScript/React | 2 | 1 | 1 | Addison
2.1 | Utilize FullCalendar.io | 3 | 1 | 1 | Addison
3.1 | "Schedule New Task" button | 2 | 1 | 1 | Janna
3.2 | Create New Task Label Button | 2 | 1 | 1 | Janna
3.3 | Display created task labels as buttons | 2 | 1 | 1 | Janna
3.4 | User-estimated task time input form | 2 | 1 | 1 | Janna
3.5 | User-inputted drive-time input form | 2 | 1 | 1 | Janna
3.6 | Task Deadline (Time/Date) Input form | 2 | 1 | 1 | Elizabeth
3.7 | Priority level buttons | 2 | 1 | 1 | Elizabeth
3.8 | Task description box | 1 | 1 | 1 | Janna
3.9 | Add Task Button | 1 | 1 | 1 | Janna
7.3 | Link Google Account to database | 2 | 2 | 1 | Anya
9.2 | Display list of tasks | 2 | 3 | 1 | Janna
9.3 | Display timer with start/stop button | 2 | 3 | 1 | Janna

## Sprint 2
Requirement ID | Description of Requirements | Story Points | Priority | Sprint No. | Team Member Assigned
4.1 | Schedule Task Button | 1 | 1 | 2 | Janna
4.2 | Scheduling Time Ranges | 2 | 1 | 2 | Janna
4.3 | Scheduling Date Ranges | 2 | 1 | 2 | Janna
4.4 | Fetch tasks from database to list on page | 3 | 1 | 2 | Janna
5.1 | Schedule task based on priority and/or past data | 8 | 1 | 2 | Hunter
5.2 | Add newly scheduled task to calendar interface | 3 | 1 | 2 | Anya
6.1 | Setup database | 5 | 1 | 2 | Addison
6.2 | Create and setup database tables | 3 | 1 | 2 | Addison
6.3 | Add sample data to database | 3 | 1 | 2 | Addison
7.1 | Link Google Account Button | 1 | 2 | 2 | Marco
7.2 | Backend logic Sign-in with Google API | 3 | 2 | 2 | Marco
7.4 | Account Signout button | 1 | 2 | 2 | Marco
7.5 | Create mock Event results | 1 | 2 | 2 | Marco
7.6 | Pull Google Calendar events to in-app calendar | 3 | 2 | 2 | Elizabeth

## Sprint 3
Requirement ID | Description of Requirements | Story Points | Priority | Sprint No. | Team Member Assigned
6.4 | Enforce Encryption on All Communications | 2 | 3 | 3 | Addison
7.7 | Create UI picklist for selecting a calendar to import | 5 | 2 | 3 | Marco
9.1 | Display task timer page | 2 | 3 | 3 | Anya
9.4 | Save task time from timer to database | 2 | 3 | 3 | Addison
9.5 | Remove task from list (without completion) | 1 | 3 | 3 | Janna
9.6 | Mark task complete | 1 | 3 | 3 | Janna
9.7 | Task completion time form | 2 | 3 | 3 | Janna
10 | Optimize web application for mobile/desktop | 5 | 3 | 3 | Addison
11 | Customizable mascot | 5 | 3 | 3 | Elizabeth

## Sprint 4
Requirement ID | Description of Requirements | Story Points | Priority | Sprint No. | Team Member Assigned
2.2 | Clean Daily Calendar View | 1 | 1 | 4 | Addison
2.3 | Clean Weekly Calendar View | 1 | 1 | 4 | Addison
2.4 | Clean Monthly Calendar View | 1 | 1 | 4 | Addison
7.7 | Push in-app scheduled events to Google calendar | 3 | 2 | 4 | Elizabeth
7.8 | Create UI picklist for selecting a calendar to import | 5 | 2 | 4 | Marco
11.2 | Add mascot customization page | 3 | 3 | 4 | Janna
11.3 | Display mascot options | 3 | 3 | 4 | Janna
11.4 | Save mascot selection in database | 2 | 3 | 4 | Janna
12.1 | Improve add task and task list user interface | 3 | 3 | 4 | Janna

## Sprint 5
Requirement ID | Description of Requirements | Story Points | Priority | Sprint No. | Team Member Assigned
11.5 | Add mascot selection to other pages | 2 | 3 | 5 | Janna
13.2 | Statistics leaderboard | 5 | 4 | 5 | Marco
14.1 | Update Home page UI/UX to a dashboard | 3 | 4 | 5 | Janna
14.2 | Display basic task information on dashboard | 3 | 4 | 5 | Janna
15 | Update UI/UX with darkmode, high dpi, etc. | 4 | 4 | 5 | Addison
15.1 | Make categories per user and show averages | 3 | 4 | 5 | Elizabeth